AI Search and Visibility Proposal for Company X

July 7, 2026

Thank you for the discussion about your SEO/GEO programs last week. Along with having a very lean team and an overload of projects, we heard three primary challenges which we can help with over the coming months:

## Brand Awareness

- Target audiences don’t necessarily know who Company X is

- Competitors are much louder and more visible in market

## AI Authority: Citations, Backlinks, Third-Party Mentions

- There is a deficit in third-party mentions, citations, and backlinks vs competitors

- Need help to: identify high-value third-party sites and placements, build repeatable programs for citations/backlinks, and compete specifically against Competitor 1 and Competitor 2 in AI/SEO

## Reporting Complexity

- Using BrightEdge and Semrush AI Toolkit, but:

  - Recent Google updates have caused high volatility in rankings and visibility

  - AI visibility scores and tracking not yet dependable and offer partial information

- Difficulty turning fragmented platform data (visibility, citations, share of voice) into executive-friendly narratives—especially for monthly metrics

- No system yet for pruning/refreshing underperforming or overlapping content,

Based on those challenges, we propose starting with an initial project for a quarter. Then as we make progress, we revisit supporting additional brand awareness and/or reporting programs.

Authority Building: Citations, Backlinks, Third-Party Mentions Project

Improve authority and positioning in AI search by increasing placements in third-party sites, citations, and backlinks. Focus on improving positioning vs Competitor 1 and Competitor 2.

We’ll focus on AI / Answer-Engine citations and deliver:

- An Insight Report mapping high authority citations and third-party mentions that rank you/competitors across four AI models (ChatGPT, Perplexity, Claude, Gemini).

- A competitive citations gap analysis

- An AI Search Visibility Roadmap

- Implementation of the roadmap

- Bi-monthly insight report updates

Details

To begin, we’ll develop/confirm/collaborate on up to 200 prompts from your ICP perspective. We’ll use your ICP and prompts to develop the Insight Report and AI Search Visibility Roadmap, using OptimizeGEO as our tech platform. Estimate two-three weeks for this phase.

We’ll also provide a competitive citations and mentions gap analysis so we can pinpoint where they are having success reaching the ICP.

We then develop your AI Search Visibility roadmap and secure agreement on the citations we’ll target and the third-party sites we’ll pursue. We’ll ensure specific competitor strategies. Estimate one-two weeks for this phase.

We’ll implement the roadmap with direct outreach. This phase will run from approval of the roadmap through the end of the quarter, approximately eight weeks.

Bi-monthly we'll provide an updated Insight Report to track progress and see if new information has emerged.

Timeline

This quarter-long project can begin as soon as scope of the project is confirmed.

# Deliverables and Fees

| Description |  |
| --- | --- |
| 1. Insight Report and map of the high-authority citations and third-party mentions that rank you/competitors across four AI models (ChatGPT, Perplexity, Claude, Gemini) - The Insight Report and map of high-authority citations will be the basis of the strategy and plan | $ |
| 2. Competitive Gap Analysis - Insight and data on the two competitors and where they are winning / losing in AI authority, citations and mentions |  |
| 3. AI Search Visibility Roadmap - The map and plan we’ll use with specific high-authority targets to secure citations and mentions. This will be approved before we begin outreach. |  |
| 4. Implementation of the roadmap - Estimating 20-30 targeted outreach contacts which convert into directory/citation placements. Once we have the Insight Report, we can finalize this number. We will actively follow up to secure placements and do a monthly link-target list refresh. |  |
| 5. Bi-monthly Insight Report update - Once the implementation is underway, we’ll provide a bi-monthly insight update along with details on progress against outreach. This is an opportunity to adjust strategy and plan. |  |